## RAID Log
RAID LOG
A RAID log is used to manage Risks, Actions, Assumptions, Issues, Decisions and Dependancies on a project.
Guidelines
All tabs have the following fields to be completed:
| Number | Record the number of the item in the log using sequential numbering.
| Date Raised | Enter the date the item was raised to the project team.
| Raised By | Enter the name or initials of the person who raised the item to the project team.
| Description | Enter a brief description.
| Owner | Enter the owner.
| Status | Enter the current status of the item. See the status guidelines table, below.
In addition, each tab has some additional information
Risks | Impact | See Risk Impact & Probability table, below.
Risks | Probability | See Risk Impact & Probability table, below.
Risks | Severity | See Risk Impact & Probability table, below.
Risks | Mitigation Type | Enter the type of mitigation action to be used. See mitigation guidelines table, below.
Risks | Detail of mitigating action to be taken | Enter further information about the mitigating action(s) required.
Risks | Actioner | Enter the name or initials of the person who will monitor the risk/undertake the mitigating action.
Assumptions | Reason for Assumption | Enter the reason the assumption has been made.
Assumptions | Action to Validate | Indicate the action required to validate whether the assumption is correct.
Assumptions | Impact if Assumption Incorrect | Indicate the impact on the project if the assumption is found to be incorrect.
Issues | Resolution/Follow On Actions | Indicate the resolution action and/or the follow on actions required.
Issues | Actual Date Closed | Enter the actual issue resolution date.
Issues | Notes | Insert additional notes and/or updates on progress.
Dependencies | Location | Indicate what will deliver the dependent item(s). e.g. another project, BAU Processes.
Dependencies | Deliverables | List the deliverables expected.
Dependencies | Delivery Date | Indicate the expected delivery date for the dependency.
Risk Impact & Probability
Major = 5 | 5 | 15 | 25
Moderate = 3 | 3 | 9 | 15
Minor =1 | 1 | 3 | 5
Impact / Probability | Possible = 1 | Probable = 3 | Almost certain = 5
Severity of Risk (Impact * Probability)
High | 15-25 | Unacceptable level of risk, requires constant active monitoring and measures to be put in place to reduce risk.
Medium | 5-9 | Acceptable level of risk exposure subject to regular active monitoring measures.
Low | 1-3 | Acceptable level of risk exposure subject to regular passive monitoring measures.
Status, Priority and Mitigation Guidelines
Priority | Assign priority:
| Critical | Issue will stop project progress if not resolved.
| High | Issue will likely move the project back in terms of budget or timeline, or will materially affect quality or scope.
| Medium | Issue will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage
| Low | Issue is expected to have a moderate effect on the project, but will require resources to address.
Status | What is the status of the issue?
| Open | The issue is currently open but has not yet been addressed.
| Work In Progress | The issue is being actively worked on to develop a resolution.
| Closed | The issue is no longer considered an active project threat and can be closed with or without resolution.
| Closed - Possible next phase | The issue is no longer an active threat but should be suggested for a future project in the Project Closure Report.
Risk Mitigation | What mitigating action should be taken?
| Avoidance | Avoid the risk. | e.g. descope risky activities from the project.
| Reduction | Reduce the risk Probability/Impact. | e.g. deliver in phases so impact of failure is reduced.
| Transfer | Outsource or insure the risk. | e.g. purchase insurance to cover failure.
| Acceptance | Accept and budget for the risk. | e.g. add to project budget to deal with risk if it occurrs.

## Risks
Risks
Number | Date Raised | Raised By | Description | Owner | Status | Impact | Probability | Severity (I*P) | Mitigation Type | Detail of mitigating action to be taken | Actioner
Note on A2: Record number using sequential numbering.
Note on B2: Record the date the risk was first raised with the project team.
Note on C2: Indicate who raised the risk.
Note on D2: Insert a brief description.
Note on E2: Indicate the name/intials of the owner.
Note on F2: Status: Open Work in Progress Closed
Note on G2: Record the Impact: Minor = 1 Moderate = 3 Major = 5
Note on H2: Record the Probability: Possible = 1 Probable = 3 Almost Certain = 5
Note on I2: Record the Severity: Green = Low = 1-3 Amber = Medium = 5-9 Red = High = 15-25
Note on J2: Mitigation Type: Avoidance = Reduce the Probability of the risk. Reduction = Reduce the Impact of the risk. Transfer = Outsource or insure the risk. Accept = Accept and budget for the risk.
Note on L2: Indicate the name/intials of the actioner(s).

## Assumptions
Assumptions
Number | Date Raised | Raised By | Description | Owner | Status | Reason for Assumption | Action to Validate | Impact if Assumption Incorrect
Note on A2: Record number using sequential numbering.
Note on B2: Record the date the assumption was first raised to the project team.
Note on C2: Indicate who raised the assumption.
Note on D2: Insert a brief description.
Note on E2: Indicate the name/intials of the owner.
Note on F2: Status: Open Work in Progress Closed
Note on G2: Insert the reason for the assumption.
Note on H2: Insert the action required to validate whether or not the assumption is correct.
Note on I2: Describe the impact on the project if the assumption is incorrect.

## Issues
Issue Log
Number | Date Raised | Raised By | Description | Owner | Status | Priority | Resolution/Follow On Actions | Actual Date Closed | Notes
Note on A2: Record number using sequential numbering.
Note on B2: Record the date the issue was first raised with the project team.
Note on C2: Indicate who raised the issue.
Note on D2: Insert a brief description.
Note on E2: Indicate the name/intials of the owner.
Note on F2: Status: Open Work in Progress Closed Closed - Possible Next Phase
Note on G2: Priority: Critical High Medium Low
Note on H2: Indicate the resolution action and/or the follow on actions required.
Note on I2: Indicate the Actual Close Date.
Note on J2: Insert additional notes and/or updates on progress.

## Dependencies
Dependencies
Number | Date Raised | Raised By | Description | Owner | Status | Priority | Location | Deliverables | Delivery Date
Note on A2: Record number using sequential numbering.
Note on B2: Record the date the dependency was first raised with the project team.
Note on C2: Indicate who raised the dependency.
Note on D2: Insert a brief description.
Note on E2: Indicate the name/intials of the owner.
Note on F2: Status: Open Work in Progress Closed
Note on G2: Priority: Critical High Medium Low
Note on H2: Indicate what will deliver the dependent item(s): Another Project BAU Processes
Note on I2: List the deliverables expected.
Note on J2: Indicate the expected delivery date for the dependency.